## Dashboard
Resume Intelligence — Product Dashboard
Quick links: Work Items ¦ Golden Set ¦ Runs ¦ Phases & Milestones ¦ Metrics
Total work items |  |  | Done |  |  | Completion %
In Progress |  |  | Blocked
Work items by Area
Area | Total | Done | In Progress | Blocked | P0 Count | Next focus | Notes
Extraction QA
UI / UX
Explainability
Backend
Prompts
Packaging
Metrics
Status counts
Status | Count
Not Started
In Progress
Blocked
Done
Next Actions (edit me)
1) Lock down extraction correctness (Phase 1) 2) Build golden set + automated report 3) Implement side panel dashboard (Phase 2)

## Work Items
ID | Phase | Area | Title | Description | Priority | Status | Owner | Created | Target Date | Effort | Dependencies | Acceptance Criteria | Notes | Links
WI-001 | Phase 1 | Extraction QA | Verify JD text passed to tailoring prompt | Instrument pipeline to persist exact extracted job text and exact prompt payload; confirm extracted text matches visible JD. | P0 | In Progress |  | 2025-12-14 |  | M |  | Run artifacts include job_extracted.txt + prompt_payload.json; manual spot-check passes on 10 sites; hashes logged.
WI-002 | Phase 1 | Extraction QA | Create Golden Set + automated diff runner | Build dataset of URLs + expected snippets/fields; automation computes similarity and flags failures. | P0 | Not Started |  | 2025-12-14 |  | L | WI-001 | Golden report produced; pass rate tracked; failures actionable with site notes.
WI-003 | Phase 2 | UI / UX | Persistent dashboard via Chrome Side Panel | Replace popup-only workflow with a Side Panel dashboard that stays open across tabs; show current tab capture and run timeline. | P0 | Not Started |  | 2025-12-14 |  | L | WI-001 | Side panel stays open when switching tabs; can Extract/Analyze from any active tab.
WI-004 | Phase 3 | Explainability | Show extracted JD + key points + change map | Expose 'what we extracted', 'what we detected', and 'what we changed' using structured tailoring JSON. | P1 | Not Started |  | 2025-12-14 |  | L | WI-003 | UI shows must-haves/nice-to-haves; bullet-to-requirement mapping; clear diffs.
WI-005 | Phase 1 | Backend | Add prompt payload & extraction artifacts to runs/ | Persist job_raw.html (optional), job_extracted.txt/json, prompt_used_*.txt, prompt_payload.json for each run. | P0 | Not Started |  | 2025-12-14 |  | M |  | Files available via /download map; popup enables download; status includes artifact counts.
WI-006 | Phase 1 | Prompt Orchestration | LLM pre-processor for prompt input | Use LLM API to convert extension output into a structured, high-signal payload before calling OpenAI. | P1 | Not Started |  | 2025-12-13
WI-007 | Phase 2 | UI / UX | Queued job analysis + chatbot for run edits | Allow users to queue job links, view run history, and chat to inspect/refine outputs (e.g., fix 1+ page LaTeX resumes by editing past runs). | P0 | Not Started |  | 2025-12-14

## Golden Set
Test ID | URL | Platform | Expected (snippet/notes) | Expected Fields (title/company/location) | Actual Extract (paste or link) | Similarity Score | Pass? | Last Test | Extractor Mode | Notes
GS-001 | [8 empty] | Auto/Manual
GS-002 | [8 empty] | Auto/Manual
GS-003 | [8 empty] | Auto/Manual
GS-004 | [8 empty] | Auto/Manual
GS-005 | [8 empty] | Auto/Manual
GS-006 | [8 empty] | Auto/Manual
GS-007 | [8 empty] | Auto/Manual
GS-008 | [8 empty] | Auto/Manual
GS-009 | [8 empty] | Auto/Manual
GS-010 | [8 empty] | Auto/Manual

## Runs
Run ID | Date | URL | Platform | Confidence | Extract Chars | Extraction Pass? | Tailor JSON Valid? | LaTeX Compile? | Total Sec | Error Summary | Artifacts Path
RUN-0001
RUN-0002
RUN-0003
RUN-0004
RUN-0005
RUN-0006
RUN-0007
RUN-0008
RUN-0009
RUN-0010
RUN-0011
RUN-0012
RUN-0013
RUN-0014
RUN-0015
RUN-0016
RUN-0017
RUN-0018
RUN-0019
RUN-0020

## Phases & Milestones
Phase | Objective | Key Deliverables | Definition of Done | Status | Start | Target | Owner | Notes
Phase 1 | Extraction correctness + QA baseline | Instrumentation artifacts; Golden set + report; Extraction pass metric | ≥90% pass on golden set; extracted text hash stored; prompt payload saved; regressions detectable | In Progress
Phase 2 | Persistent dashboard UX (side panel) | Side panel UI; cross-tab capture list; run timeline; downloads/history | Side panel stays open across tab switches; can Extract/Analyze from any tab; no state loss | Not Started
Phase 3 | Explainability & trust | Key points, must/nice, change map, before/after diffs; requirement→bullet mapping | Users can see what changed and why for each section; no hallucinated requirements | Not Started
Phase 4 | Product polish & freemium readiness | Limits/gating; onboarding; settings; metrics; upsell surfaces | Clear free tier limits; stable analytics; subscription flow ready (even if mocked) | Not Started

## Metrics
Product & Reliability Metrics
Metric | Definition | Value | Notes
Extraction pass rate (Runs) | % of runs where Extraction Pass?=YES
Tailor JSON validity rate | % of runs where Tailor JSON Valid?=YES
LaTeX compile success rate | % of runs where LaTeX Compile?=YES
Avg total seconds | Average of Total Sec
Golden set pass rate | % of Golden Set rows marked PASS